## Slide 1: Core Group Agenda, 13/01/2022
General update
  COVID situation and format of the event
2. Technical update
  Registrations
  Working groups: update and next steps
  Online events: information and update
  Business Declaration
3. Next milestones

## Slide 2: General update
COVID situation and format of the event

## Slide 3: Technical update
  Registration of participants
  Working groups: update and next steps
  Online events: information and update
  Business Declaration

## Slide 4: Registration Platform
1176 registrations since 16th December
Invitation and flyer have been sent to 8,500+ contacts in our database. The registration platform is now open.

## Slide 5: Working groups

## Slide 6: Working Groups – Update
Progress since last CG meeting (6 January)
WG meeting #3 ongoing this week
Validation of all speakers, moderators and topics for HLP
Start of process for Business Declaration
Discussion with WG members regarding online events, B2B/B2G, signature ceremonies
Planned work
Invitations to be sent to speakers
Preparation of draft Business Declaration
Preparation of WG meeting #4

## Slide 7: WG Outputs and Timeline
High Level Panel
December
January 2022
February 2022
Topics/Speakers/Moderators
Sponsored Guests
15 Dec
7-11 Feb.
Speaker briefing
15 Dec
Business Declaration
Business
Outcomes
&Call Action 1st Draft
21 Jan
PHYSICAL EVENT
Online workshop/
Seminar
1 Hybrid
5 Online, incl. group B2B/B2G
Submission of
Events topic/ speakers
13 Jan (deadline)
Event Finalised
Speaker briefing
7-11 Feb.
Trade Fair
(Online booths)
Registration open 16th Dec
Online Booth Set up
Signatures/
Ceremonies
22 Dec
28 Jan
Outreach
Finalisation
30 Jan
ONLINE EVENT
List
Suggested list by WG
Indiv. B2B/B2Gs w/ registration
7-11 Feb.
List
1 Feb.
28 Jan
2nd Draft
Final
Draft
Business
Declaration
3-15 Jan
22 Dec
28 Jan
Final list
14 Feb
Final
BO/CA
18 Feb
SUMMIT
17 Jan
Set up EABF
Drafting
Committtee

## Slide 8: Working Groups – Update
10/01 Fashion 9:30am Health 2pm | Youth 9:30am Digital 11:30am Finance 2pm | PANAF 11am Agri-food 2pm | Infrastructure 9am EU-Africa VCs 11am | Raw material 9:30am Energy 11am Automotive 2pm
17/01 Fashion 9:30am | Youth 9:30am Digital 11:30am | Agri-food 2pm | EU-Africa VCs 11am | Raw material 9:30am Automotive 2pm
24/01 Health 2pm | Finance 2pm | PANAF 11am | Infrastructure 9am | Energy 11am
31/01 |  |  |  | 
07/02 |  |  |  | 
Full WG meeting #4
Monday | Tuesday | Wednesday | Thursday | Friday
WG meetings calendar January/February 2022
Full WG meeting #3
Potential additional WG meeting (depending on needs)

## Slide 9: Online events

## Slide 10: OVERALL ANALYSIS
220 REGISTERED APPLICATIONS BREAKDOWN

## Slide 11: OVERALL ANALYSIS

## Slide 12: HIGH-LEVEL HYBRID EVENTS

## Slide 13: HIGH-LEVEL HYBRID EVENTS
  6 high-level hybrid events registered from 8

## Slide 14: PARTNERS

## Slide 15: PARTNERS APPLICATIONS (1)
39 Partners | 39 Partners |  |  | 
AeTrade Group | Africa Economic Zones Organization (AEZO) | Direction générale du Trésor | Afroskills | 3D Netinfo ' DigiArt Living Lab
AfroChampions | Africa-EU Energy Partnership (AEEP) | Global Young Leaders Organization | Alliance for Rural Electrification | Trans Africa Rail Corperation (TARC)
Pan African Chamber of Commerce and Industry | AFRUIBANA | Hellenic Ministry of Foreign Affairs | Consultative Group to Assist the Poor (CGAP) | Inferastructure Support Mechanism
East African Chamber of Commerce, Industry and Agriculture | ANIMA Investment Network | BUSINESSMED | PharmAccess Fondation (Group) | TradeMalta
 | Commonwealth Alliance of Young Entrepreneurs-West Africa | Federation of European Publishers | Reseau femmes africaines pour le developpement durable | Université Paris-Dauphine PSL
 | Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH | Patronat G5 SAHEL | Women in Africa Initiative | Innovea Hubs & Innovea Development Foundation
 | AfrIPI | PEEP - Policy Experimentation & Evaluation Platform | Youth Action Hub Guinea - UNCTAD | EU-Japan Centre for Industrial Cooperation
 | MEDEF International | ENRICH in Africa | United Nations Industrial Development Organization (UNIDO) | German-African Business Association (Afrika-Verein)
 | African Circular Economy Network | EU Africa RISE | UNICEF | 
  39 partners selected for the first wave

## Slide 16: PARTNERS APPLICATIONS (2)
Africa Business Council | European Commission - DG JRC
African Union Commission | European Commission – DG INTPA
Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) | European Commission - DG Education, Culture, Youth and Sport
Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH | European Commission – INTPA A1
EDFI | European Commission – DG ENV
European Entrepreneurs CEA-PME | European Commission
  Applications for partnership coming from individual companies or British institutions were invalidated
36 Partners applications to validate |  |  |  | 
AREEA | CEN CENELEC | European International Contractors (EIC) | Irish Whiskey Association | Organisation des femmes africaines de la diaspora (OFAD)
BDI | COCOBOD | FIDA-Fédération Internationale de la Diaspora Afar | LA VERTICALE AME | Spain Chamber
BIC AFRICA | Confédération des entreprises algériennes | Gambia Chamber of Commerce and Industry | LAPSSET Corridor Development Authority | TradeMark East AFrica
BPW | ECOWAS Commission | GLOBAL YOUTH ACTION NETWORK/TAKINGIT GLOBAL | Mairie de Moroni) | Tycune Media (Pty) - academic
RES4Africa | European Business Summits | International Trade Center - Ethical Fashion Initiative | Office of Valorization and Relation with the industry at the Ministry of High School and Scientific Research | Université HEC TCHAD
  Proposed selection for the second wave:

## Slide 17: WORKSHOPS & SEMINARS

## Slide 18: WORKSHOPS AND SEMINARS PROPOSED SELECTION (1)
Category | Organization name | Pays | Project in a few lines
Civil society | Alliance for Rural Electrification | Belgium | Workshop/side-session on "Creating jobs and empowering women and youth via renewable electrification in Africa "
Institution / Government | UNICEF | Belgium | Reimagining education in Sub-Saharan Africa means bringing digital technologies for learning to every child, especially the most vulnerable and marginalized. It means transforming how children and young people learn by introducing digital skills that can expand their career prospects. Digital technology can also empower teachers and other educators in formal, informal and home learning settings. It can ensure data are collected and analysed in real time to monitor class attendance and improve school management. And it can provide parents with guidance to make sure their children are enrolled in school, receive learning support at home and ultimately complete their education.
Institution / Government | Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) | Germany | Women Entrepreneurship for Africa (WE4A) is a programme jointly co-financed by the European Union (EU) and the Organisation of African, Caribbean, and Pacific State (OACPS) together with the Federal Ministry for Economic Cooperation and Development (BMZ)
Institution / Government | Direction générale du Trésor France | France | Dedicated event to support the launch of the Alliance for Entrepreneurship in Africa, which gathers multiple multilateral and bilateral development institutions to accelerate the development of the private sector in Africa, with a specific focus on provid
Institution / Government | EU-Japan Centre for Industrial Cooperation | Japan | EU-Japan business cooperation in/with Africa. EU and Japanese businesses are increasingly forging partnerships to operate jointly in/with Africa in a number of sectors, e.g. green transition, digital transformation. These EU-Japan business cooperation
Institution / Government | European Commission DG GROW | Belgium | Sustainable investment: What does it mean for companies? Companies are expected to make sustainable investments (green and social), thus adhering to a sustainable business model.
Professional organisation | African Circular Economy Network | South Africa | The African Circular Economy Network (ACEN) is a community of circular economy professionals which aims to build a restorative African economy that generates well-being and prosperity inclusive of all its people through new forms of economic production.
Professional organisation | BUSINESSMED | Tunisia | Our activities are mainly focused on the private sector in the Mediterranean. As one of the major economic development clusters, we must support our affiliates not only to strengthen themselves but also to develop sustainable value chains between EU and AU.
Professional organisation | Federation of European Publishers | Belgium | Business dialogues between European publishers and African publishers on how best to promote translation rights between the two continents, how can we improve the sharing of experiences, what is the state of digital publishing in Europe and in Africa.
Professional organisation | Women in Africa Initiative | Nigeria | Women in Africa Initiative is the foremost platform promoting women entrepreneurs across Africa and building an eco-system that increases women's contribution to Africa's economic transformation.
Think tank | 3D Netinfo ' DigiArt Living Lab | Tunisia | Créé en Tunisie, 3D Netinfo est la première école d’Art et de technologie en Afrique spécialisée dans la formation aux métiers du codage créatif et de la production de l’image de synthèse 3D.
Think tank | RES4Africa | Italy | RES4Africa (Renewable Energy Solutions for Africa) is a Foundation that works in support of Africa’s just energy transition in order to achieve SDG7, ensuring access to affordable, reliable, sustainable and modern energy for all.
Civil society | Innovea Hubs & Innovea Development Foundation | Nigeria | Energy Transfer Hub for Efficiency and Renewables seeks to transform skills, improve efficiency and productivity in energy solutions as a statrategic approach towards transitioning from fossil based energy to renewable energy.
Civil society | EU Africa RISE | Belgium | Africa RISE (Reform for Investment and Sustainable Economies) is a demand-led technical assistance facility that supports inclusive and sustainable growth and decent work in Eastern Africa, Southern Africa, and the Indian Ocean region. It promotes macro-e
Civil society | Global Young Leaders Organization | Tunisia | How women entrepreneurs in Africa can access finance
Institution / Government | LA VERTICALE AME | France | Projet ZESS : vers un modèle africain de zones économiques spéciales et sécurisées (ZESS) en partenariat avec l'Europe
Academics / Researchers / Students | Université Paris-Dauphine PSL | France | Through a collaboration approach between African and European academia and professionals, co-designing curricula, conceiving hybrid methodology (on-line and face-to-face) for the various types of training delivered (certificate, high-level seminars...). A
  100 applications for workshops and seminars. 17 workshops were selected for the first wave.

## Slide 19: WORKSHOPS AND SEMINARS PROPOSED SELECTION (2)
Category | Organization name | Pays | Project in a few lines
Academics / Researchers / Students | Africa Energy Services Group | Rwanda | wastes disposal is a big challenge for environment. My project is of transforming used car tires into black carbon which can be used in road construction .
Multinational | African Electronic Trade Group | Eswatini | The AeTrade Group is a social enterprise with a strategic partnership with the African Union and major private sector organisations in Africa, including MSMEs, women and youth. Our objective is to promote inclusive approaches and partnerships between Afri
Civil society – NGO, Youth organisation, Women organisation, Association | AFRUIBANA | France | As a pan-African association of producers and exporters of bananas and other fruits from Côte d'Ivoire, Cameroon and Ghana, we would like to organise a workshop on the notion of fair valuation of African agricultural production and the need to see th
Institution / Government | Agency for Business and Development - GIZ | Germany | Suggestion fits into the topic "Financing Africas Sustainable Growth" and highlights concrete possiblities to finance projects in Africa by bringing together decision makers from EU, IFIs and high level company representatives in a business brea
Institution / Government | British Council | Kenya | Environmental and social concerns are beginning to dent demand for ‘fast fashion’, with its attendant toxicity for the planet and for human rights consumers are increasingly looking for more sustainable options that cause less harm to the envi
Multinational | CGAP | Belgium | CGAP and EIB will co-organize a side session on the future of microfinance opportunities and challenges.
Professional organisation | COCOBOD | Ghana | Agribusiness in the Cocoa value chain
Civil society – NGO, Youth organisation, Women organisation, Association | European International Contractors (EIC) | Germany | Bringing together esteemed experts representing the African-European Financing Architecture for Development, this roundtable shall investigate in four discussion rounds of about 25 minutes each, how to address infrastructure development needs, how to oper
Institution / Government | GIZ | Germany | tbd
Institution / Government | Hellenic Ministry of Foreign Affairs | Greece | "Green shipping for clean energy: market prerequisites and green energy transition opportunities for African and EU partners” (autonomous event in hybrid format)
Civil society – NGO, Youth organisation, Women organisation, Association | Irish Whiskey Association | Ireland | Representing Irish whiskey, the largest and fastest-growing EU spirits category in Africa
Academics / Researchers / Students | Office of Valorization and Relation with the industry at the Ministry of High School and Scientific Research) | Cote d'Ivoire | My commitment,s as Deputy Director of Valorization and Relation with Industry at the Ministry of High school and Scientific research in Côte d'Ivoire, is to build the public-private partnership ecosystem for R&D in Côte d'Ivoire: oneline m
Civil society – NGO, Youth organisation, Women organisation, Association | Organisation des femmes africaines de la diaspora (OFAD) | France | Un atelier sur Femmes ,Entrepreneuriat et Développement en Afrique. L'AFRIQUE est le continent où les femmes créent le plus au monde cependant elles font face aux problèmes de formation et de financement. Il nous a paru normal dans u
Civil society – NGO, Youth organisation, Women organisation, Association | PEEP - Policy Experimentation & Evaluation Platform | Portugal | www.sg4africa.org - is a pan-Africa research project on savings groups coordinated by our NGO For Development (recognized with the ONG-D status from the Portuguese foreign office). We would like to promote the consortium and the research that we have now
Civil society – NGO, Youth organisation, Women organisation, Association | PharmAccess Group | Netherlands | PharmAccess Group is an international non-profit organization dedicated to strengthening health systems in Africa (focus on Ghana, Kenya, Nigeria and Tanzania) through an integrated approach, public-private partnerships and by leveraging digital technolog
Institution / Government | Spain Chamber | Spain | To explore means of strengthening Africa Europe partnerships, and the role of the private sector to respond to disrupted markets and ensure post-COVID 19 economic resilience and steady recovery driven by strong, vibrant, and dynamic Private Sector. The E
  We propose to preselect 50 workshops for the second wave. Some applications need to be further examined in coordination with Working groups.

## Slide 20: WORKSHOPS AND SEMINARS PROPOSED SELECTION (3)
Category | Organization name | Pays | Project in a few lines
Professional organisation | Africa Business Council | Egypt | The Africa Business Council ( AfBC) is established as an institution in line with the African Union Assembly Decision on Boosting Intra African trade and Fast Tracking the Establishment of the African Continental Free Trade Area. AfBC founding Vision is
Professional organisation | Africa Business Council | Egypt | The Africa Business Council ( AfBC) is established as an institution in line with the African Union Assembly Decision on Boosting Intra African trade and Fast Tracking the Establishment of the African Continental Free Trade Area. AfBC founding Vision is
Professional organisation | Africa Business Council | Egypt | The Africa Business Council ( AfBC) is established as an institution in line with the African Union Assembly Decision on Boosting Intra African trade and Fast Tracking the Establishment of the African Continental Free Trade Area. AfBC founding Vision is
Institution / Government | AFRICA ECONOMIC ZONES ORGANIZATION (AEZO) | Morocco | SEZ Workshop
Institution / Government | Africa Economic Zones Organization (AEZO) | Morocco | Africa Economic Zones Organization (AEZO) is a continental association representing of leading public and private institutions in charge of the Development, Management and Promotion of Economic Zones in Africa. Founded in November 2015 by Tanger Med Group
Institution / Government | Africa-EU Energy Partnership | Germany | 
Civil society – NGO, Youth organisation, Women organisation, Association | Africa-EU Energy Partnership (AEEP) | Germany | The Africa-EU Energy Partnership (AEEP) was launched by African and European Heads of State in 2007 at the AU-EU Summit in Lisbon, Portugal. A central partnership of the Joint Africa-EU Strategy, the AEEP is the key political platform through which both c
Civil society – NGO, Youth organisation, Women organisation, Association | Africa-Europe Foundation and British Council | Belgium | The British Council and the Africa-Europe Foundation (AEF) are accelerating shared efforts to reinforce youth voice, agency and leadership at the heart of the UN Climate Change Conference (COP) and the Africa-Europe partnership in 2022. In this context
Institution / Government | African Union Commission | Ethiopia | Host a platform that will allow young African Innovators to engage with stakeholders and venture capitalists. Activities will include a pitching for young nominated entrepreneurs, a mid-level dialogue and a workshop on the opportunities for young innovato
Institution / Government | AfrIPI | Spain | he AfrIPI project, funded under the Pan-African Program (and funded by the DG INTPA), aims to boost the continental economic integration through strengthening and improving the systems for Intellectual Property Rights (IPR) creation, protection, utilizati
Civil society – NGO, Youth organisation, Women organisation, Association | AfroChampions | Ghana | 
Professional organisation | ANIMA Investment Network | France | An exchange workshop on a key innovation sector for Africa to : a.Promote innovators and public and private innovation support organisations in Africa b.Share advice and best practices, including from THE NEXT SOCIETY achievements and successes c.Present replicable national policies, tech hub models and solutions developed by startups in the continent that contribute to improving innovation in key sectors (e-health, e-education, green tech, agri-food, energy, transport).
Civil society – NGO, Youth organisation, Women organisation, Association | BDI | Germany | Together with our project partner, the COMESA Business Council (CBC), BDI is fostering regional integration in the COMESA region. In our joint workshop with CBC, we will discuss how to boost the economic relations between the EU and the COMESA region.
Civil society – NGO, Youth organisation, Women organisation, Association | BDI - Federation of German Industries | Germany | BDI is engaged within Africa together with the Business Scouts for Development programme (GIZ) and our partners in East Africa fostering on regional integration, value chains, job creation. Female business leaders play an important role in the economic re
Institution / Government | European Commission – DG INTPA | Belgium | AfCFTA, a game changer
Professional organisation | East African Chamber of Commerce, Industry and Agriculture | Kenya | In 2011 at the unveiling of Program for Infrastructure Development for Africa (PIDA), it was noted that Africa's biggest challenge to its economic development is mainly the infrastructure gap that has exacerbated inaccessibility and Intra-Africa Trade
Institution / Government | European Commission - DG JRC | Italy | The JRC has composed a Photovoltaic Decentralised Energy Investment (PV-DEI) Index that is highly relevant to the Business Forum. The PV-DEI measures how favourable it is to invest in decentralised photovoltaic (PV) mini-grids in a given African country

## Slide 21: WORKSHOPS AND SEMINARS PROPOSED SELECTION (4)
Category | Organization name | Pays | Project in a few lines
Professional organisation | EDFI | Belgium | The Association of European Development Finance Institutions (EDFI) is delighted to contribute as a strategic partner to the EABF. Our 15 member institutions have a long-standing track record of investing in the sustainable development of the private sect
Institution / Government | European Commission | Belgium | Breaking through the product regulatory glass ceiling and boosting trade and investment in Africa
Institution / Government | European Commission | Belgium | Project: Following the Pandora papers leak and the international deal on corporate taxation, the webinar will provide a platform for engagement about current international tax issues for stakeholders from tax authorities and businesses from Europe, Africa
Institution / Government | European Commission - DG Education, Culture, Youth and Sport | Belgium | In the context of the EABF, a “Youth and entrepreneurship panel” will focus on business creation. DG EAC considers that a workshop on education-business cooperation would usefully complement it. Entrepreneurship closely links also to skills de
Institution / Government | European Commission - DG ENV | Belgium | Circularity
Professional organisation | European Entrepreneurs CEA-PME | Belgium | 
Professional organisation | Federation of West Africa Chamber of Commerce and Industry | Nigeria | ECOWAS Community enterprise experiences as a tool to deepening continental integration under the framework of AfCFTA and to attract FDI in Africa.
Civil society – NGO, Youth organisation, Women organisation, Association | FIDA-Fédération Internationale de la Diaspora Afar | Belgium | Exposition des produits artisanales et traditionnels de la culture Afar. Organisation d'une conférence sur le rôle de la Diaspora dans la reconstruction post-conflit en Ethiopie. Présentation de chants et danses traditionnelles Afars.
Institution / Government | GIZ | Germany | The proposed investment roundtable aims to bring together mutliple stakeholders from the EC, AU-C, Smart Africa, EU-MS, international financial institutions and the private sector to discuss how to enhance investments in sustainable digital infrastructure
Institution / Government | Infrastructure Support Mechanism Technical Assistance to AU | Ethiopia | The Round table on Business opportunities in the Infrastructure and transport value chains will present the priority corridors in Africa and enable private sectors operators in infrastructure and transport sectors to brainstorm on business and investment
Professional organisation | MEDEF International | France | Green hydrogen: New opportunities for the EU-Africa low-carbon energy relationship and Africa's integration in energy value chains
Professional organisation | MEDEF International | France | digital technology for vocational training in Africa
Professional organisation | MEDEF International | France | Challenges and opportunities of cybersecurity in Africa
Professional organisation | MEDEF International | France | Online event : What technological mix to quickly bridge the digital divide in Africa? The example of the education sector.
Professional organisation | Pan African Chamber of Commerce and Industry | Ethiopia | Access to trade finance, or financial instruments and means of payment for international transactions, can improve the ability of small and medium-sized enterprises (SMEs) to engage in international activities and participate in global value chains (GVCs)
Professional organisation | Pan African Chamber of Commerce and Industry [PACCI] | Ethiopia | Reliable Logistics Data through Technology Integration This session will focus on new and advanced technologies that are used to track logistics and its contribution to building sustainable value chain in Africa.
Start-up | The AeTrade Group | United States | Under the theme of Infrastructure and Connectivity theme in the EUABF-22; the AeTrade Group plans to conduct a panel discussion on deploying Smart Logistics, Fulfilment and Transport Network for Africa.

## Slide 22: BOOTHS

## Slide 23: BOOTHS (1)
ORGANISATION NAME | 
Africa Economic Zones Organization (AEZO) | European Business and Innovation Centre Network (EBN)
Africa Energy Services Group | European Business Summits
Africa-EU Energy Partnership (AEEP) | European Commission - DG GROW
African Circular Economy Network | Footprints Africa Limited
African Energy Commission (AFREC) | German-African Business Association (Afrika-Verein)
AfrIPI | IBRIZ SAS
Afroskills | Innovea Hubs & Innovea Development Foundation
Alliance for Rural Electrification | KING OF KINGS MULTI-INVESTMENTS & CONSULTANCY FARM LTD
ANG CAPITAL GAMBIA LTD | Malta Business
BE Kollective Consulting Limited | Office of Valorization and Relation with the industry at the Ministry of High School and Scientific Research)
BUSINESSMED | Pan African Chamber of Commerce and Industry
Delegation of German Industry and Commerce EA | PEEP - Policy Experimentation & Evaluation Platform
DIFFA | Reseau femmes africaines pour le developpement durable
Direction générale du Trésor | Rockland Energy
Europan Commission - DG-INTPA.E2 (VET) | Spiefabrique 360° UG
E-ACTIV | Trans Africa Rail Corperation (TARC)
ECO Capacity Exchange | United Nations Industrial Development Organization (UNIDO)
Elétric Mobility Cape verde | Vodafone
Entreprise sotransproma de l'Aïr | Women in Africa Initiative
EU Africa RISE | 
  134 applications for booths. 40 applications were selected for the first wave.

## Slide 24: BOOTHS (2)
ORGANISATION NAME | 
Africa Business Council - Building Business Linkages between European and Africa Stakeholders and Business Organizations (E-Commerce, Building Capacity Training, Promoting Entrepreneurship, and facilitating Trade and Exhibitions) | COBASA
Africa Business Council - Role of Media in Promoting Africa Europe Businesses | Computaz Systems Limited
AFRICA ECONOMIC ZONES ORGANIZATION (AEZO) | Confédération des entreprises algériennes
Africa GreenCo | Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH
Africa-Europe Foundation and British Council | DG INTPA
African Electronic Trade Group - Cloud Computing Infrastructure, Research and Innovation | Durandel Limited
African-Nordic Business Platform | East African Chamber of Commerce, Industry and Agriculture
africon | EDFI
AfroChampions | EU-Japan Centre for Industrial Cooperation
AfroGreenTech | European Commission - European Cluster Collaboration Platform (ECCP) and the Enterprise Europe Network (EEN)
AFRUIBANA | European Commission - current international tax issues for stakeholders from tax authorities and businesses from Europe, Africa
Agrific | European Commission - How a Composite index can help businesses to scale up investments in clean energy in SSA
ANIMA Investment Network | European Entrepreneurs CEA-PME
Argo Baum | Eutelsat
Asante Mama Natural Products Ltd | EY
Authentic Zanzibar Experience (AZE) | Fédération des Entreprises du Congo
BIC AFRICA | Federation of West Africa Chamber of Commerce and Industry
BPW | FIDA-Fédération Internationale de la Diaspora Afar
BPW MADRID | Footprints Africa
Cellular Expert UAB | Fundi App
  We propose to select 78 applications for booths for the second wave. 16 applications were duplicate.

## Slide 25: BOOTHS (3)
ORGANISATION NAME | 
Gambia Women,s Chamber of Commerce, The Gambia West Africa | Niusline Media Limited
GAUFF Gmbh & Co Engineering KG | Nopal Jegg Enterprise
GIZ | Omnia Education Partnerships
GLOBAL YOUTH ACTION NETWORK/TAKINGIT GLOBAL | Organisation des femmes africaines de la diaspora (OFAD)
Government | Pharm-Bio Technology and Traditional Medicine Center at Mbarara University of Science and Technology
Hotbox Marketing Solutions | Prototipi
IFBPW | Royal arts
International Trade Center - Ethical Fashion Initiative | SahtiCare / Vitah
IU International University of Applied Sciences | Solidaridad Europe
JIGUTAM AGENCIES | STUDIO KÄ
LA VERTICALE AME | Sustainable Finance Risk Consulting GmbH
Lake Victoria Basin Talent Development and Adolescent Health | The AeTrade Group - deploying Smart Logistics, Fulfilment and Transport Network for Africa.
LAPSSET Corridor Development Authority | TradeMark East AFrica
Mairie de Moroni | Tycune Media (Pty) Ltd
MEDEF International - digital technology for vocational training in Africa | Université HEC TCHAD
MEDEF International - Green hydrogen: New opportunities for the EU-Africa low-carbon energy relationship and Africa's integration in energy value chains | Vobiss Solutions Limited
MOUVEMENT DES ENTREPRISES DE FRANCE INTERNATIONAL | VOLKENO SARL
MUTSIMOTO MOTOR CO. LTD | Wastezon
Ngurumah Tours and Travel Ltd | Youth Action Hub Guinea - UNCTAD

## Slide 26: B2B / B2G

## Slide 27: B2B/B2G (1)
Type | Organization name | Country | Subject B2B / B2G
B2B | AFRUIBANA | France | Promotion en Europe de la production de fruits africains.
 | Commonwealth Alliance of Young Entrepreneurs-West Africa | Ghana | Equity or Debt Investors
 | Cuanu Resources & Technical Services Ltd | Nigeria | Technology Entrepreneurship Ngozi Okonjo Iweala
 | FAEDA | Senegal | Possibilité de parler de business avec des entrepreneurs et des investissements, présentation de possibilité d'investissement
B2G | E-Tech Resources Inc. | Namibia | How can dedicated sustainable value chain partners for the supply of critical materials be detected? (For investors, off-takers and public stakeholders)
 | EUD in Gambia (EEAS-BANJUL) | Gambia | Invest in Gambia
 | Global Wind Energy Council (GWEC) | Kenya | We would be interested in meeting any African Government Authority, including utilities, ministries of energy and regulators to discuss creating an enabling environment for renewables, particularly wind energy.
 | Patronat G5 SAHEL | Mauritania | Espoir pour le Sahel - infrastructures - corridor désenclavement - énergie
 | Siemens Healthcare | Belgium | Policy-makers active in development and healthcare; healthcare providers; development agencies. Topics to be discussed are: digital solutions supporting knowledge-sharing in the healthcare sector; south-south collaboration; importance of training and education to ensure access to healthcare.
 | The European Chamber of Commerce in Sudan | Sudan | Senior officials from both private and pubic sectors who are responsible for, or interested in, digital identity as a service.
 | Vuka Connect Pty Ltd | South Africa | Economic development, specifically black empowerment. key people in States procurement
 | Winwin africa | France | we would propose to discuss about sport /culture and development issues
 | AeTrade Group | Pan Africa | Scalable digital innovation from Africa. Cross cutting issues will be covered with 6 AeTrade Group representatives
  138 applications for B2B/B2G. 13 applications were selected for the first wave.

## Slide 28: B2B/B2G (2)
Organization name | Country | Subject B2B / B2G
Africa Business Council | Egypt | African and European Stakeholders. Building Business Linkages between European and Africa Stakeholders, and Business Organizations (E-Commerce, Building Capacity Training, Promoting Entrepreneurship, and facilitating Trade and Exhibitions)
Africa Business Council | Egypt | AfBC would like to have B2B/B2G meetings with African and European Investors to discuss African-Europe business collaboration and entrepreneurship.
Africa Business Council | Egypt | Role of Media in Promoting Africa Europe Businesses"
Africa In Colors | Rwanda | We will be discussing everything culture and creative industry, opportunities and the future of it on the African continent
AfroGreenTech | Cameroon | We would like to meet regulators, startups, entrepreneurs and investors to have a meeting on global economy, real estate, health, education, financial inclusion and future of work.
CEN CENELEC | Belgium | Africa’s industrialization strategy
Delegation of the EU to Tunisia | Tunisia | topics: investment climate in Tunisia + benchmarking Study comparing the competitiveness of countries North Africa + success stories from a selection of private investors in Tunisia
East African Chamber of Commerce, Industry and Agriculture | Kenya | Entities/people who fall under the Energy and Transportation sector.
European Commission | Belgium | The meeting should focus on networking between European and African SMEs, clusters and other business organizations and their members.
European Commission | Belgium | This Forum offers an opportunity to outreach with both the EU and African businesses, to discuss and showcase how the regulatory tools, the use of international standards and a proportionate, risk-based approach to determine the least burdensome conformity assessment procedures can boost their business opportunities.
  We propose to preselect 28 applications for the second wave. Some applications need to be further examined in coordination with Working groups.

## Slide 29: B2B/B2G (3)
Organization name | Country | Subject B2B / B2G
European Commission | Belgium | Business tax representatives and tax authorities in Africa and EU. International organizations, regional organizations in EU and Africa.
European Entrepreneurs CEA-PME | Belgium | B2G - African governments interested in developing their small business sector transferring our experience, best practices and know-how to their countries, European governments interested to develop trade with and investment in Africa by their national SMEs, taking advantage of our experience, networks and tools.
European International Contractors (EIC) | Germany | DG INTPA, EIB, AUDA NEPAD, AfDB, EIC Infrastructure financing, Global Gateway
Eutelsat | France | We would like to see governments as well as entrepreneurs from both continents attend to discuss the issue of broadband connectivity via satellite in Africa at an affordable price and for full coverage.
FCA Investments | Finland | Issues that we like to discuss include: - How can we jointly provide the sustainable SMEs in African LDCs a competitive edge beyond access to finance? - How do the African countries – with the support from international actors best support the SMEs and their ecosystems? - What is the role of private sector of developed countries in supporting the LDCs in areas such as digitalization? - how to realize the promise of macro-level initiatives such as the Investing in Young Business in Africa to contribute to national economies and the SDGs alike?
GLOBAL YOUTH ACTION NETWORK/TAKINGIT GLOBAL | Ghana | ENERGY TRANSITION MEDICAL INNOVATION TRANS CONTINENTAL EDUCATION POST COVID DIGITAL ENTREPRENEURSHIP START UP PARTNERSHIPS
IU International University of Applied Sciences | Germany | Topic: Realizing the potential of African youth to sustainably strengthen African economies through higher education (working title)
LAPSSET Corridor Development Authority | Kenya | Government Infrastructure Investors
MEDEF International | France | Cybersecurity in Africa
MEDx eHealthCenter | Netherlands | Topic 1 to be discussed: How can the private sector support the agenda of UHC by 2030. Topic 2: How can we stimulate North - South Collaboration for an optimal implementation of UHC programs by 2030

## Slide 30: B2B/B2G (4)
Organization name | Country | Subject B2B / B2G
MOUVEMENT DES ENTREPRISES DE FRANCE INTERNATIONAL | France | agro-food processing in the Sahel Organizers: MEDEF International + UPAS (union of G5 Sahel business federations)
PwC | France | Maximizing benefits and improving International Development and Support for Africa. (we can address the entire topic or focus on some specific sectors)
SahtiCare / Vitah | Tunisia | Develop customized solutions for healthcare-related businesses. Business Partnerships and Potential Agreements to expand our business in Africa and Europe. Investments/Grants Opportunities.
Solidaridad Europe | Netherlands | We would like to organize a small meeting between African and European Businesses, relevant NGOs and interested civil partners. We would like to discuss the creation of sustainable supply chains between African countries and the European Union, with a focus on cotton, textiles and the Ethiopian context.
STUDIO KÄ | Cote d'Ivoire | Business to business: The place of African content on the world stage, what are the levers of success? Attendees : Investors and CEOs Business to Government: Making African cultural heritage the foundation of a new economy. Attendees : Ministries of culture, Government, Investors
Sustainable Finance Risk Consulting GmbH | Germany | We would like to have an active role at the side events. Two workshop proposals have been submitted. One will focus at the presentation of the product suite of AEGF - the other one on the multiplication of the structure of AEGF which was set up a pilot to leverage the guarantee provision of the European Commission
TradeMark East AFrica | Kenya | Key Questions to guide topics of discussion: •how to warm up businesses, development partners, investors for the idea of the Green Corridor? • What are new and ambitious ideas we can put forward and get interest from the business community?
Youth Action Hub Guinea - UNCTAD | Guinea | Bailleurs de fonds et organisations de jeunesse

## Slide 31: SHOWCASES (1)
Organization name | Country | Subject B2B / B2G
14km | France | MIGRATION - MOBILITY TO AFRICA. I AM READY TO BE A SPEAKER CONCERNING THIS TOPIC.
AfroChampions | Ghana | 
Agrific | Nigeria | I will like to see Venture capitalists, Agro Allied industries CEO's, Private Equity investors and Businesses
AISBL MBEKA Makosso Joseph | Belgium | Le gouvernement Congolais sur les sujets de, éducation, développement, formation professionnelle en alternance, travail, jeunesse et subsidiaire
Asante Mama Natural Products Ltd | Uganda | I would like to meet Development Cooperation departments, Financing Institutions and EU cocoa or chocolate importing companies. I would like to discuss investing in cocoa processing factory worth €7.4 million in Uganda.
Authentic Zanzibar Experience (AZE) | Tanzania | Investors, funders, international partners organization, and buyers.
Cellular Expert UAB | Lithuania | African businesses working with geospatial information and infrastructure planning to discuss the topic of availability and use of GIS data to aid development of telecommunications infrastructure.
COBASA | South Africa | agrobusiness investors
Computaz Systems Limited | Kenya | Government representatives in Agro sector
Cre8tiveRevolution Group | Netherlands | Government officials representing SME, Creative Industries and Economic Affairs
Durandel Limited | Nigeria | Global Aquaculture Industry stakeholders from from across the private, public and social sectors.
EDFI | Belgium | We are still considering if/how we want to organise a roundtable and will revert to you with a definite answer/more information as soon as possible.
  We propose to preselect 34 applications for showcases for the second wave. Some applications need to be further examined in coordination with Working groups.

## Slide 32: SHOWCASES (2)
Organization name | Country | Subject B2B / B2G
European Commission - DG Education, Culture, Youth and Sport | Belgium | 
Fundi App | Tanzania | EU Africa High-level Pitch Event - ‘Physical Startup pitching in front of the African Europe biggest Venture Capitals
Gambia Chamber of Commerce and Industry | Gambia | 
GAUFF Gmbh & Co Engineering KG | Senegal | Business to gouvernement. I would like to see countries decisions makers.
GIZ | Germany | multiple stakeholders from the EC, EU-MS, AU-C private sector companies, international financial institutions and representatives of partner countries from the Africa region.
GIZ (Gesellschaft für Internationale Zusammenarbeit) | Germany | Policy makers, business managers, financial institutions, development practitioners and youth representatives from Africa, Europe and beyond.
Government | Belgium | Agriculture (smart agriculture, agribusiness, fresh produce) Innovation and digitalisation Renewable energy manufacturing (pharmaceuticals)
Hotbox Marketing Solutions | Zimbabwe | I would like to see Venture Capitalists and Angel Investors and would like to discuss about how we can scale the product to help all other SADC countries and many African countries.
IFBPW | Italy | 
Kenya Airports Authority | Kenya | Potential investors on airport landslide facilities
MUTSIMOTO MOTOR CO. LTD | Kenya | Anyone who is looking for partnerships in Kenya especially in the Automotive and Food insustry.

## Slide 33: SHOWCASES (3)
Organization name | Country | Subject B2B / B2G
Ngurumah Tours and Travel Ltd | Kenya | Travel, Tourism and Logistics companies and individuals.
Omnia Education Partnerships | Finland | Government and business representatives interested in scalable, high quality vocational training and upskilling for green and blue economy.
Organisation des femmes africaines de la diaspora (OFAD) | France | Les investisseurs, les dirigeants africains et européens
Pong Agencies Limited | Kenya | Real estate developers looking to invest infrastructure on Kenya. We provide IT infrastructure for new buildings / projects. I will also be looking for tech companies looking to establish a presence in East Africa.
Royal arts | Burundi | Thé investors
TPSD | Senegal | 
Tycune Media (Pty) Ltd | South Africa | Top-level decision and policy makers from the EU and the AU, and senior business leaders working to enhance the EU-Africa trade and investment relationship really interested in the following topic and unique opportunity: "Winning the war against poverty and hunger - Implementation Proposals"
Université HEC TCHAD | Chad | Le développement durable et le changement climatique au bassin du lac Tchad. La crise économique, humanitaire et l'impact du changement climatique sur le quotidien des lacustres.
VOLKENO SARL | Senegal | Tout acteur porteur d'idée ou de projet à la recherche d'un partenaire technique.
WEGA - Women in Germany and Africa | Germany | We want to discuss with women entrepreneurs and policy makers who can influence the mind shift and social norms how we can foster women’s access to jobs in the energy transformation in Africa.
ZNND Group | South Africa | Members of the AU /EU and heads of African states

## Slide 34: SIGNATURE CEREMONIES

## Slide 35: SIGNATURE CEREMONIES (1)
Organisation name | Project description
Afrochampion/Afrexim Bank | Fashion - MOU between Afrexim bank and the Association of Textile Producers of Portugal, to partner on the creation of the industrial parks on manufacturing
Direction générale du Trésor - France | Dedicated event to support the launch of the Alliance for Entrepreneurship in Africa, which gathers multiple multilateral and bilateral development institutions to accelerate the development of the private sector in Africa, with a specific focus on provid
EDFI | Signature of the EDFI MSME Guarantee, contracted by EDFI MC under EFSD+ (EUR80 m commitment from the EU)​
 | Official launch of the AgriFI Country Windows (Ghana, ACP, Tanzania and Sri Lanka) (in aggregate, EUR80m commitment from the EU)​
 | ElectriFI top-up for Kenya (EUR 23m commitment from the EU) ​
 | I&M Bank Kenya (USD 10m), a (mock) signing from FMO as part of the Nasira EFSD facility. This is Nasira’s third transaction in Kenya, which sum up to USD 75m in total.
  35 applications for signature ceremonies. 3 applications were selected for the first wave.

## Slide 36: SIGNATURE CEREMONIES (2)
Organisation name | Project description
AfBC and the Spain Chamber of Commerce | Collaboration between Spain Private Sector and Africa- Promoting Entrepreneurship/ SMEs /Skills Development & Promoting trade between Spain & Africa
AfBC / ITC | Collaboration on international Trade & AfCFTA
AfBC and the Italian Expo Group - IEG | Collaboration between IEG & AfBC in the fields of promoting and marketing of Private Sector in Africa and Europe in the fields of Jewellery Industry, Mining, Agri -Food and Tourism through the biggest specialized fairs and exhibiitions organized by IEG
AfBC and BPW | International Federation of Business and Professional Women - Collaboration of AfBC and BPW on Women Empowerment & Empowering Women in Trade and Access to Market in Africa and Europe
AfBC and AE Trade Group | Collaboration on Digital Economy and Empowering SMEs in Africa
  We propose to select 5 applications for the second wave. Some applications need to be further examined.

## Slide 37: Business declaration
Business Outcomes & Call for action

## Slide 38: Guidelines - Business Declaration
BUSINESS DECLARATION = The Joint EU Africa Business Declaration is a joint statement prepared by the European and African private sector as a key deliverable of the EU Africa Business Forums and is presented to the HoS EU Africa Summit.
12 Business Outcomes
1 per working group
Designed and implemented by business
12 Calls for action to the Summit
1 per working group
A unique advocacy opportunity to influence policy making
Business Declaration
+
=
Who is in charge of drafting and How?
  Drafting Committee: EBO/ABO Chairs or the small selected technical team
Ensures overall coherence and responsible for ensuring validation)
EABF Joint Business Declaration Drafting Committee Composition:
    ABO: AfBC, PACCI and Afrochampions and Business Africa
    EBO: CEA-PMEA, EBCAM, Business Europe, Eurochambres
Working Group Level
EABF Global Level

## Slide 39: Guidelines - Business Declaration
Time and Sequencing of Meeting
  The Business Declaration will be presented by 1 ABO and 1 EBO Drafting Committee representative on the 18 February at the Summit
Working Group Level
EABF Global Level
  WG Meeting #3
    Discuss the methodology and set up a WG drafting team  By 21 January 2022 1st Draft
  WG Meeting #4
    2nd Draft Business Outcome and Call for Action  By 28 January 2022
  Final Business Outcomes and Call for Action submitted to the Drafting Committee by all WGs By 1 February 2022
  Set up of the Drafting Committee  By 17 January 2022
  Iterative meetings of Drafting Committee to prepare the overall Business Declaration (17, 24, 31 January) and (7, 14 February)
  Finalized by the EABF Business Declaration Drafting Committee on 14 February 2022 and fine tuning 15, 16, 17

## Slide 40: Business Outcome & Calls for Action
EACH WG Chairs
Business Outcome
Call Action
Drafting Team (EBO/ABO)
Consolidate WG Inputs
Ensure Coherence Across 12 Business Declarations
EU Africa Summit
Validation of the Business Declaration
How can I provide input?
  Each working group member can input on proposed Business Outcome and Call for Action
  Working group member organisations are encouraged to consult their members on the proposed declarations
How will it be used once finalised?
  Private sector organizations across both continents to mainstream key priorities into respective strategies, action plans, ect.
  Development partners to use for designing funding instruments and programmes
  Development finance institutions to mainstream into funding policies and design financing instruments
  Government institutions to mainstream into policies and programmes

## Slide 41: Business Outcome & Calls for Action
Example of Business Declaration - Health WG
Business Outcome: Set up a pan-African Fund for R&D support for Start-Up in pharmaceutical production
Call for Action: Reduction of bound tariffs on inputs such as APIs and pharmaceutical
Guiding points for drafting team:
Encapsulate all WG deliverables
Concise, Actionable and Time-bound and Participatory
Monitoring framework

## Slide 42: Key Milestones

## Slide 43: Critical path & milestones Overall Event
WG Members
Completed all online events and deliverables
Awards, etc, WG activities for the event
Finalise travel & logistic arrangements
Finalise conference kits
Complete test with Panellists & moderators
Complete Media & com
WG Members
Pursue WG meetings for mapping, topics, agenda, speakers, guest
Contact & secure speakers' participation
Draft sponsored guest list
Preliminary List of all online events
Preliminary List of partner Stands
Preliminary List of B2Bs
WG Members
Mobilise the private sector, partners and stakeholders
Provide list of WG members and participants list
First sponsored guest list
Business Declaration
HLP Topic/Speakers/Ect
Organising Team
Prepare guidelines
Finalise & dispatch flyers & PR Tools
Organise CG& WG meetings
Make Website ready
Start registration process
By 15 Dec. 2021
By End Dec. 2021
By 30 Jan. 2022
WG Members
Fine tuning of HLP and all deliverables
Installation in Partner Booths Square
Speakers Briefing
Mock run of pitches
Set up online profile
Organisation Team
Post final programme
Complete security & health
Complete pre-recorded and streamed digital
Complete Mock sessions
By 11 Feb 2022
Managing the Forum
Communication & press
Post forum reporting
Post-event information material
14 -18+ Feb 2022
Setup of event foundation & start registration/HLP finalised
Completion of HLP preparation/Preparation Online Events
Completion of all WG deliveries
Completion of event preparation
Go-live

## Slide 44: Annex - Agenda

## Slide 45: Agenda for the Physical EABF22 as part of the Africa Europe week
Thursday 17
Wednesday 16
AFRICA EUROPE WEEK
EVENTS
ONLINE PLATFORM
OPEN 24/7 FULL FIVE DAYS OF THE WEEK
AFRICA WEEK & EABF HIGH LEVEL OPENING
EABF PLENARY PANELS
EABF PLENARY PANELS
& CLOSING
PHYSICAL TRACK
200 max. participants
EU
AFRICA
SUMMIT
CEO & HEADS OF STATE AND GOVERNMENT INTERACTION (TBC)
ONLINE TRACK
6,000 expected participants
AFRICA WEEK EVENT
AFRICA
EUROPE
WEEK
EVENTS
EU
AFRICA
SUMMIT
Friday 18
Tuesday 15
EABF HYBRID WORKSHOPS

## Slide 46: Agenda for the Physical Event
WEDNESDAY 16
THURSDAY 17
Opening Session
with Europe-Africa Week on Tuesday
The Pan-African Opportunity
Financing Africa’s Sustainable Growth
1030
1130
1145
1300
1315
1430
EABF Networking lunch
1445
1600
1630
1745
Integrating EU & Africa Value Chains
Youth & Entrepreneurship
1030
1130
1145
1300
1315
1400
Africa Europe Week & EABF Networking lunch
1415
1530
Sustainable Raw Materials & Local Value Creation
Automotive & Sustainable Mobility
Working Closing Session
1600
1715
Interaction Session with CEOs and Heads of States and Governments
1900
2100
TBC
Sustainability embedded in all Panels
Digital Innovation for Job Creation & Sustainability
Healthcare & Pharmaceuticals
Infrastructure & Connectivity
Sustainable Agri-food Systems
Ethical Fashion & Apparel Industry
Sustainable Energy
Enabling Framework
Value Chains
People & Planet
Interpretation in 4 languages
Arabic, English, French & Portuguese

## Slide 47: Agenda for the Physical Event
WEDNESDAY 16
THURSDAY 17
The pan African opportunity
Financing Africa’s sustainable growth
1030
1130
1145
1300
1315
1430
EABF Networking lunch
1445
1600
1630
1745
Integrating EU & Africa value chains
Youth & entrepreneurship
1030
1130
1145
1300
1315
1400
Africa Europe Week & EABF Networking lunch
1415
1530
Sustainable Raw Materials & Local Value Creation
Automotive & Sustainable Mobility
Working closing session
1600
1715
Interaction session with CEOs and Heads of States and Governments
1900
2100
Sustainability embedded in all Panels
Digital Innovation for Job Creation & Sustainability
Healthcare & Pharmaceuticals
Infrastructure & Connectivity
Sustainable agri-food systems
Ethical Fashion & Apparel Industry
Sustainable Energy
Enabling Framework
Value Chains
People & Planet
ITC Value Chains Restitution
The EU opportunity
Horizontal wrap-ups
(eg Sustainability, Women, SMEs…)
Online events possible except first morning session and closing
TBC